## Tabelle1
To-Dos - Recruiting Events (especially workshops + activities)
Tasks | Subtasks | Description | Description | Priority
1. Definition of a potential university measure
Define the objective of the measure |  | Objective, e.g.: Short-term recruiting for selected positions Employer Branding/ positioning in the market Format Case Study Lecture-style presentation | HR | 6 months in advance
Coordination with the department |  | What is the objective from the department's perspective that is of interest? Which target group should be addressed? What format/event/activity is of interest? … | HR | 6 months in advance
2. Clarification of internal capacity
Is there man-power available in the team? |  | Does the team have the capacity to conduct an event? Who could be a potential contact person? Are the potential contact persons willing to participate in the event? | Department | 6 months in advance
3. Clarification of the framework conditions
Event format |  | For example: Lecture Case Study Workshop Social Activities, e.g., Buddy Bash, dining out, ... … | HR | 3 months in advance
Date and duration |  |  | HR | 3 months in advance
| Clarify data within the team |  | HR | 3 months in advance
| Send appointment blockers/invitations |  | HR | 3 months in advance
Overview of costs |  |  | HR | 3 months in advance
| Costs for the format |  | HR | 3 months in advance
| Costs for catering/snacks, etc. |  | HR | 2 months in advance
| Costs for the activity |  | HR | 2 months in advance
Determine the number of potential participants |  | What is the minimum and maximum number of participants for the selected format? HR's suggestion Coordination with the department | HR & department | 1 month in advance
If necessary, opening Slack channel/ Teams channel for communication |  |  | HR | 1 month in advance
4. Preparation of the event
Prepare the case for the workshop |  |  | Department | 2 months in advance
If necessary, book an external room |  | Where should the event/parts of the event take place? Internally > Office External room | HR | 3 months in advance
| Research and cost comparison | Size > maximum group size Location/ accessibility Technical equipment (connections, TV size, projector...) Flipchart, pens, etc. Beverages? Other amenities | HR | 3 months in advance
| Inspection of the room |  | HR | 3 months in advance
| Booking of the room |  | HR | 2 months in advance
| Inclusion of address details in the appointment blocker/invitation |  | HR | 2 months in advance
If necessary, book internal room |  |  | HR | 2 months in advance
Plan a social activity |  |  | HR | 2 months in advance
| Research |  | HR | 2 months in advance
| Selection & consultation with the department |  | HR & department | 2 months in advance
| Booking/ Organization of the activity |  | HR | 2 months in advance
Organisation Snacks / Catering |  |  | HR | 1 month in advance
| Order snacks |  | HR | 1 month in advance
| Research restaurant/ caterer for the evening |  | HR | 1 month in advance
| Selection/Booking Restaurant/ Caterer for the evening |  | HR | 1 month in advance
| Plan and order drinks for the workshop + afterwards |  | HR | 1 month in advance
Plan materials |  |  | HR | 1 month in advance
| Blocks |  | HR | 1 month in advance
| Pens |  | HR | 1 month in advance
| Potentially recruiting materials |  | HR | 1 month in advance
| Technical equipment |  | HR | 1 month in advance
| If necessary, flipcharts, index cards, post-it ́s, etc. |  | HR | 1 month in advance
Planning the journey |  | Examples: Travel to the external location Travel to the activity Travel to the restaurant | HR | 1 month in advance
| If necessary, booking rental car |  | HR | 1 month in advance
| Inclusion details in the appointment blocker |  | HR | 1 month in advance
| Information to the department |  | HR | 1 month in advance
Goodie bags |  |  | HR | 1 month in advance
| Collection of ideas |  | HR | 2 months in advance
| Selection of goodies |  | HR | 1 month in advance
| Ordering the goodies |  | HR | 1 month in advance
| Prepare business cards/ LinkedIn QR codes |  | HR | 1-2 weeks in advance
| Prepare personal messages |  | HR | 1-2 weeks in advance
| Packing the goodie bags | Including notepad & pen + see above | HR | 1-2 weeks in advance
Creation of name badges |  |  | HR | 1-2 weeks in advance
Preparation of consent forms for photos |  |  | HR | 1-2 weeks in advance
Create a landing page |  | Contact valantic | HR | 1 month in advance
5. Advertising
Create images/ digital flyers |  | Format compatible for LinkedIn and Instagram | HR | 1 month in advance
| Collectin ideas |  | HR | 2 months in advance
| Pass on to the respective marketing department |  | HR | 1 month in advance
| Storage/backing up in the folder |  | HR | 1-2 weeks in advance
Optional: Collaborate with student initiatives |  | Examples: Newsletter, Instagram advertising for the event, LinkedIn advertising for the event | HR | 2 months in advance
| Research the possibilities |  | HR | 2 months in advance
| Selection of options |  | HR | 1 month in advance
| Newsletter | Create text, proofread, add images | HR | 1 month in advance
| Repost |  | HR | 1 month in advance
LinkedIn Post |  |  | HR | 2 months in advance
| Write |  | HR | 2 months in advance
| Posting on behalf of CC |  | HR | 1 month in advance
| Posting valantic |  | HR | 1 month in advance
| Posting from your own account |  | HR | 1 month in advance
Instagram Post |  |  | HR | 2 months in advance
| Announcement valantic marketing | Consider timeline, etc. | HR | 1 month in advance
| Prepare |  | HR | 1 month in advance
| Send material | Consider format | HR | 1 month in advance
6. Selection of participants
Define application channel |  | Where and to whom are the candidates' applications submitted? Email; Landing page; HR contact person? | HR | 2 months in advance
Pre-selection of CVs |  |  | HR | 1 month in advance
Selection/consultation of participants with the department |  |  | HR & department | 1 month in advance
Contact selected participants |  |  | HR | 1 month in advance
| Formulate text |  | HR | 1 month in advance
| Send invitations |  | HR | 1 month in advance
Table with details about the participants |  | As preparation for the profiles; starting point for discussions: Name, age, course of study, university, interests How interesting for us? Other remarks (e.g., already in process, etc.) | HR | 1-2 weeks in advance
| Creation of the table |  | HR | 1-2 weeks in advance
| Placing in the folder |  | HR | 1-2 weeks in advance
| Forward to the department |  | HR | 1-2 weeks in advance
| Print if necessary |  | HR | 1-2 weeks in advance
Certificates of participation |  |  | HR | 1-2 weeks in advance
| Prepare |  | HR | 1-2 weeks in advance
| Personalize |  | HR | 1-2 weeks in advance
| Print & Sign |  | HR | 1-2 weeks in advance
7. Event day
Channel message regarding consideration in the internal premises |  |  | HR | Event Day
Preparation of the room |  |  | HR | Event Day
| Snacks |  | HR | Event Day
| Beverages |  | HR | Event Day
| Glasses etc. |  | HR | Event Day
| Blocks |  | HR | Event Day
| Pens |  | HR | Event Day
| Recruiting materials |  | HR | Event Day
| Whiteboard | Clean beforehand & 'Warm Welcome' message | HR | Event Day
| Goodie bags |  | HR | Event Day
| Name tags |  | HR | Event Day
Lounge music |  |  | HR | Event Day
Prepare after-event food |  | Napkins, plates, cutlery, etc. | HR | Event Day
Take photos |  |  | HR & department | Event Day
Have consent forms for photos signed |  |  | HR | Event Day
Distribute participation certificates |  |  | HR | Event Day
8. Follow-up to the event
Storing and sorting photos |  |  | HR | After the event
Scan and file consent forms for the photos |  |  | HR | After the event
Contact participants with a "thank you" email |  |  | HR | After the event
if necessary, advertise specific job positions |  |  | HR | After the event
Document particularly interesting participants and stay in the loop |  | Calendar reminders; enter into the applicant management system; etc. | HR | After the event
Conduct a retrospective |  | What should be retained? What should be adjusted? What do I wish for the future? Preparation of the event Execution of the event Follow-up of the event | HR | After the event
| Appointment with the department |  | HR | After the event
| Prepare |  | HR | After the event
| Document |  | HR | After the event
| Deriving optimization potential |  | HR | After the event
Share the success of the event with the team |  |  | HR | After the event
Social media post with pictures etc. |  |  | HR | After the event
| Creation incl. selection of photos |  | HR | After the event
| Posting on behalf of CC |  | HR | After the event
| Posting valantic |  | HR | After the event

## Tabelle2
HR
HR & department
Departement